## Slide 1
Consumer market entry readiness engagement
Requirements Gathering Project Kickoff Meeting

## Slide 2
Our understanding of Engagement Scope
Capabilities, processes, and systems to enable Industrobots to launch new robot products in the consumer market
Business Capabilities
Manufacturing
Supply chain and supply
chain management
Business Processes
Repair technician network development and management
Systems -Business-level and backend systems
Product-level software
Mobile device app for controlling and customizing the IDROID
Robot interface to Amazon
Alexa
Business Capabilities
Consumer Marketing
Consumer distribution channels and channel management
Consumer buying experience
Business and co-marketing
Partnership with major alarm/security monitoring providers
Business Processes
Consumer technical support
Automated Robot maintenance
Systems-Business-level and Backend systems
Robot software Upgrade/Patch
Integration with major alarm/security monitoring providers
Distribution and Management
Robot-based home security
CRM system for consumer Sales and service
In-Scope
Out-of-Scope

## Slide 3: Requirements Gathering - High Level Project Plan
Key idea
Stake holder Interviews
Brainstorming sessions
BPMN
Key idea
Change strategy gap analysis As-is-to-be
Key idea
Workshops for determining level of Importance
Tasks priority
Timing of effort
Resource Availability
Key idea
Communicate with key stakeholders
Conduct review workshops
Extraction
and
Gathering
Documentation
and
Analyze
Prioritization
Sign
In
Approval
Initial set of requirements from all stakeholders and sources
Complete, Organized set of requirements
Prioritized Requirements
Approved set of requirements to submit to the design team/phase
Key Methods
Key Deliverables

## Slide 4
Client team engagement requests
Our project kicks off with organizing a set of interviews and a document request.
As-is To-be
Specifications
Designs
Product plans
IT Systems design and documentation
Marketing and Sales plans
API Documentation
Home Security providers Interface
Key Account
Executives/Managers
Marketing agency
Channel partner
Home Security provider
Marketing Head
Sales Head
IT Head
Product Development head
Customer Support Head
Marketing Team
Sales Team
IT Team
Product Team
Customer Support Team
Internal Stakeholders
External Stakeholders
Document Requests
Interview Requests